## Project plan (Initial) (hidden)
| Start date (First task to be initiated) |  | 2016-10-03 |  |  | Project Plan
| End of Phase 1 (First loan to be disbursed) |  | 2016-12-25 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
| End of Phase 2 (Operations are set, 100 loans disbursed) |  | 2017-02-01 | time axis 2016-10-03 to 2017-02-12
| Business line | Sub-lines | Start | Finish | Status | 2016-10-03: W 1; 2016-10-10: W 2; 2016-10-17: W 3; 2016-10-24: W 4; 2016-10-31: W 5; 2016-11-07: W 6; 2016-11-14: W 7; 2016-11-21: W 8; 2016-11-28: W 9; 2016-12-05: W 10; 2016-12-12: W 11; 2016-12-19: W 12; 2016-12-26: W 13; 2017-01-02: W 14; 2017-01-09: W 15; 2017-01-16: W 16; 2017-01-23: W 17; 2017-01-30: W18; 2017-02-06: W 19
[6 empty] | 2016-10-03 | [6 empty] | 2016-10-10 | [6 empty] | 2016-10-17 | [6 empty] | 2016-10-24 | [6 empty] | 2016-10-31 | [6 empty] | 2016-11-07 | [6 empty] | 2016-11-14 | [6 empty] | 2016-11-21 | [6 empty] | 2016-11-28 | [6 empty] | 2016-12-05 | [6 empty] | 2016-12-12 | [6 empty] | 2016-12-19 | [6 empty] | 2016-12-26 | [6 empty] | 2017-01-02 | [6 empty] | 2017-01-09 | [6 empty] | 2017-01-16 | [6 empty] | 2017-01-23 | [6 empty] | 2017-01-30 | [6 empty] | 2017-02-06
[6 empty] | 2016-10-09 | [6 empty] | 2016-10-16 | [6 empty] | 2016-10-23 | [6 empty] | 2016-10-30 | [6 empty] | 2016-11-06 | [6 empty] | 2016-11-13 | [6 empty] | 2016-11-20 | [6 empty] | 2016-11-27 | [6 empty] | 2016-12-04 | [6 empty] | 2016-12-11 | [6 empty] | 2016-12-18 | [6 empty] | 2016-12-25 | [6 empty] | 2017-01-01 | [6 empty] | 2017-01-08 | [6 empty] | 2017-01-15 | [6 empty] | 2017-01-22 | [6 empty] | 2017-01-29 | [6 empty] | 2017-02-05 | [6 empty] | 2017-02-12
Phase 1
1 | Product&BP | Product and business process are defined | #REF! | #REF! | 8
2 | Risk | Credit policy and related documents are defined | #REF! | #REF! | 8
3 | Operations | Local catalogues and batch file templates are developed and translated | #REF! | #REF! | 8
4 | Finance | Accounting policy is formulated | #REF! | #REF! | #REF!
5 | Legal | Local companies are legally set-up | #REF! | #REF! | 8
6 | Finance | Accounts are opened and funded | #REF! | #REF! | #REF!
7 | HR | Lead Generation Company (LGC) Start team is hired | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF!
9 | Legal | Customer & Entities Legal agreements are drafted | #REF! | #REF! | #REF!
10 | Marketing | User-friendly design for customer docs is created | #REF! | #REF! | #REF!
11 | Operations | Office Renovation is finished | #REF! | #REF! | 8
12 | IT | Office Infrastructure is set | #REF! | #REF! | #REF!
13 | IT | Initial IT infrastructure (SMS gateway, Data center) is set | #REF! | #REF! | #REF!
14 | Finance | Ad-hoc payments are provided (lease, equipment, Internet, SMS, DC) | #REF! | #REF! | #REF!
15 | IT | Website is developed | #REF! | #REF! | #REF!
16 | Digital Sales | Media plan is prepared | #REF! | #REF! | #REF!
17 | Marketing | Media content (banners, campaings, etc.) is developed | #REF! | #REF! | #REF!
18 | Digital Sales | Social media presence is set up | #REF! | #REF! | #REF!
19 | IT | Terrasoft Software is customized for local market | #REF! | #REF! | #REF!
Phase 2
20 | HR | Initial Collection team is hired | 2016-11-18 | 2017-01-27 | 0
21 | HR | Staff management standards are implemented | #REF! | #REF! | #REF!
22 | HR | Mass team recruitment and training is arranged | #REF! | #REF! | #REF!
23 | Digital Sales | Reports & Analytics are set up | 2016-12-15 | 2016-12-24 | 0
24 | Operations | Call Center Team performance is handled | #REF! | #REF! | #REF!
25 | Risk | Phone Verification Team performance is handled | 2016-12-01 | 2017-01-01 | 0
26 | Risk | Collection team performance is handled | 2017-01-12 | 2017-02-11 | 0
27 | Finance | Agreement with General Ledger is signed | 2016-12-18 | 2017-01-02 | 0
28 | HR | Agreement with Payroll agent is signed | 2016-12-15 | 2016-12-27 | 0
29 | Operations | Agreements with disbursement & repayment agents are signed | 2016-12-15 | 2017-01-20 | 0
30 | IT | IT infrastructure is completed | 0 | 2017-01-30 | 0
31 | Finance | Payments for IT infrastructure is made | 2016-01-15 | 2017-01-07 | 0
Legend:
Green bar represents sublines where more than 50% of tasks performed according to schedule
Yellow bar represents sublines where there are 50% of tasks to be finilized within max 7 days (pay attention)
Red bar represents sublines where there are 50% of tasks to be finilized within 3 days or delayed
Dark Gray vertical line shows current date
Pink vertical line shows the end of Phase 1

## Launch plan - Phase 1
| Start date (First task to be initiated) |  |  | 2016-10-03 | Launch plan - Phase 1
| End of Phase 1 (First loan to be disbursed) |  |  | 2016-12-25
Progress
№ | Company | Business line | Sub line | Task | Document/ Link | Responsible MM | Status | Duration, days | Start fact | Finish fact |  | 68.8% |  | Task status | Days to the end of Phase 1
1 |  | Product&BP |  | Product and business process are defined | [9 empty] | 8
1.1 |  | Product&BP | Product and business process are defined | Product Parameters Document are created and approved | Product Parameters | Dziatkovskiy | done | 5 | 2016-10-10 | 2016-10-15 | 1 | 1 | #REF! | 8 | #REF!
1.2 |  | Product&BP | Product and business process are defined | First Sale Business Process are created and approved | First Sale BP | Dziatkovskiy | done | 10 | 2016-10-10 |  | 1 | 1 | #REF! | 8 | #REF!
1.3 |  | Product&BP | Product and business process are defined | Repeat Sale Business Process are created and approved |  | Dziatkovskiy | in progress | 5 | 2016-10-27 |  | 1 | 0.5 | #REF! |  | #REF!
1.4 |  | Product&BP | Product and business process are defined | Loan application form in XLS is created and approved | Loan application | Dziatkovskiy | done | 5 | 2016-10-12 | 2016-10-17 | 1 | 1 | #REF! | 8 | #REF!
1.5 |  | Product&BP | Product and business process are defined | a List of parameters for Printing forms is created | Printing forms | Dziatkovskiy | done | 10 | 2016-10-10 | 2016-10-14 | 1 | 1 | #REF! | 8 | #REF!
1.6 |  | Product&BP | Product and business process are defined | SMS content is created | SMS content | Dziatkovskiy | done | 3 | 2016-10-05 | 2016-10-10 | 1 | 1 | #REF! | 8 | #REF!
2 |  | Risk |  | Credit policy and related documents are defined | [8 empty] | #REF! | 8
2.1 |  | Risk | Credit policy and related documents are defined | Credit policy is created and approved | Internal & Public credit policies | Dziatkovskiy | done | 5 | 2016-10-10 | 2016-10-14 | 1 | 1 | #REF! | 8 | #REF!
2.2 |  | Risk | Credit policy and related documents are defined | Phone Verification manual is created and approved | Verification procedures | Dziatkovskiy | done | 5 | 2016-10-19 | 2016-10-28 | 1 | 1 | #REF! | 8 | #REF!
2.3 |  | Risk | Credit policy and related documents are defined | Calling policy is created and approved | Calling policy | Dziatkovskiy | done | 5 | 2016-10-28 | 2016-11-07 | 1 | 1 | #REF! | 8 | #REF!
3 |  | Operations |  | Local catalogues and batch file templates are developed and translated | [8 empty] | #REF! | 8
3.1 |  | Operations | Local directories, translations, and batch files | a list of catalogues (Cities, Banks, Dial numbers, etc.) for Terrasoft is developed | Directories | Sai Hnin Aung | done | 2 | 2016-10-05 | 2016-10-07 | 1 | 1 | #REF! | 8 | #REF!
3.2 |  | Operations | Local directories, translations, and batch files | Loan application & catalogues are translated into local language | Loan application | Sai Hnin Aung | done | 5 | #REF! | 2016-10-22 | 1 | 1 | #REF! | 8 | #REF!
3.3 |  | Operations | Local directories, translations, and batch files | Batch file template (required for loan disbursement) is created | MCM Batch file | Dziatkovskiy | done | 5 | 2016-10-10 | 2016-10-18 | 1 | 1 | #REF! | 8 | #REF!
4 |  | Finance |  | Accounting policy is formulated | [8 empty] | #REF! | #REF!
4.1 |  | Finance | Accounting policy is formulated | Accounting policy is formulated |  | Myo Min | in progress | 10 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
5 |  | Legal |  | Local companies are legally set-up | [8 empty] | #REF! | 8
5.1 |  | Legal | Local companies are legally set-up | Lead Generation Company | documents of incorporation | Sai Hnin Aug | Done | 40 | 2016-10-18 | 2016-10-20 | 1 | 1 | #REF! | 8 | #REF!
5.2 |  | Legal | Local companies are legally set-up | Company Registration | documents of incorporation | Sai Hnin Aug | Done | 40 | 2016-10-18 | 2016-10-20 | 1 | 1 | #REF! | 8 | #REF!
5.3 |  | Legal | Local companies are legally set-up | Pawnshop (PS) | documents of incorporation | Sai Hnin Aug | Done | 40 |  | 2016-09-15 | 1 | 1 | #REF! | 8 | #REF!
5.4 |  | Legal | Local companies are legally set-up | Nominee for Pawnshop License |  | Sai Hnin Aug | Done | 40 |  | 2016-09-15 | 1 | 1 | #REF! | 8 | #REF!
5.5 |  | Legal | Local companies are legally set-up | Pawnshop license granted |  | Sai Hnin Aug | Done | 40 |  | 2016-09-15 | 1 | 1 | #REF! | 8 | #REF!
5.6 |  | Legal | Local companies are legally set-up | NEW Company Registration ( for Pawnshop funding) - Myanmar advanced technology (MAT) |  | Sai Hnin Aug | in progress | 25 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
5.7 |  | Legal | Local companies are legally set-up | NEW Company Registration - 2 director names , their passport copies, addresses |  | Sai Hnin Aug | in progress | 1 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
5.8 |  | Legal | Local companies are legally set-up | Amount of authorized capital injected (50k) |  | Sai Hnin Aug | in progress | 1 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
5.9 |  | Legal | Local companies are legally set-up | Company registration certification |  | Sai Hnin Aug | in progress | 1 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
5.10 |  | Legal | Local companies are legally set-up | Company address |  | Sai Hnin Aug | in progress | 1 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
5.11 |  | Legal | Local companies are legally set-up | Company letter head |  | Sai Hnin Aug | in progress | 1 | 2016-11-04 |  | 1 | 0.5 | #REF! | #REF! | #REF!
5.12 |  | Legal | Local companies are legally set-up | Proposed 3 different names for new company in Myanmar |  | Sai Hnin Aug | in progress | 1 | 2016-11-07 |  | 1 | 0.5 | #REF! | #REF! | #REF!
6 |  | Finance |  | Accounts are opened and funded | [8 empty] | #REF! | #REF!
6.3 |  | Finance | Accounts are opened and funded | Bank account for OPEX is opened |  | Sai Hnin Aung | done | 6 | 2016-11-04 |  | 1 | 1 | #REF! | 8 | #REF!
6.4 |  | Finance | Accounts are opened and funded | Bank account that to be used to collect payments is opened |  | Sai Hnin Aung | done | 6 | 2016-11-07 |  | 1 | 1 | #REF! | 8 | #REF!
6.5 |  | Finance | Accounts are opened and funded | Bank account for OPEX is opened |  | Sai Hnin Aung | not started | 6 | 2016-11-04 |  | 1 | 0 | #REF! | #REF! | #REF!
6.6 |  | Finance | Accounts are opened and funded | Bank account that to be used to disburse loans is opened |  | Sai Hnin Aung | done | 6 | 2016-11-07 |  | 1 | 1 | #REF! | 8 | #REF!
6.7 |  | Finance | Accounts are opened and funded | Bank account that to be used to collect payments is opened |  | Sai Hnin Aung | done | 6 | 2016-11-07 |  | 1 | 1 | #REF! | 8 | #REF!
6.8 |  | Finance | Accounts are opened and funded | Getting tokens and sending it to RH |  | Dziatkovskiy | done | 2 |  |  | 1 | 1 | #REF! | 8 | #REF!
6.9 |  | Finance | Accounts are opened and funded | Getting tokens and sending it to RH |  | Dziatkovskiy | not started | 2 |  |  | 1 | 0 | #REF! | #REF! | #REF!
6.10 |  | Finance | Accounts are opened and funded | Initial amount for Business development received |  | Dziatkovskiy | done | 4 |  |  | 1 | 1 | #REF! | 8 | #REF!
6.11 |  | Finance | Accounts are opened and funded | Initial amount for Business development received |  | Dziatkovskiy | not started | 4 |  |  | 1 | 0 | #REF! | #REF! | #REF!
6.12 |  | Finance | Accounts are opened and funded | Initial amount for Portfolio financing received |  | Dziatkovskiy | not started | 4 |  |  | 1 | 0 | #REF! | #REF! | #REF!
7 |  | HR |  | Lead Generation Company (LGC) Start team is hired | [8 empty] | #REF! | #REF!
7.1 |  | HR | Doctor Kyat (LGC) staff docs | Employment agreement is drafted |  | Head of HR | in progress | 7 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
7.2 |  | HR | Doctor Kyat (LGC) Management Start team | Local citizen for a position of Pawnshop Nominee is defined | M Zaw Naw | Dziatkovskiy | done | 0 | 2016-10-20 | 2016-10-20 | 1 | 1 | #REF! | 8 | #REF!
7.3 |  | HR | Doctor Kyat (LGC) Management Start team | Recruit a Head of Legal and compliance - Job offer signed | J P Nan Tong | Sai Hnin Aung | done | 20 | #REF! | 2016-11-18 | 1 | 1 | #REF! | 8 | #REF!
7.4 |  | HR | Doctor Kyat (LGC) Management Start team | Head of Legal and complience officially joined the team |  | Sai Hnin Aung | done | 0 |  |  | 1 | 1 | #REF! | 8 | #REF!
7.5 |  | HR | Doctor Kyat (LGC) Management Start team | Recruit Head of Digital Marketing - Job offer signed | Thar Htet Aung | Dziatkovskiy | done | 20 | 2016-10-18 | 2016-11-24 | 1 | 1 | #REF! | 8 | #REF!
7.6 |  | HR | Doctor Kyat (LGC) Management Start team | Head of Digital Marketing officially joined the team |  | Dziatkovskiy | done | 0 |  | 2016-11-24 | 1 | 1 | #REF! | 8 | #REF!
7.7 |  | HR | Doctor Kyat (LGC) Management Start team | Recruit Head of Accounting Offer - Job offer signed | Myo Min | Sai Hnin Aung | done | 27 | #REF! | 2016-11-14 | 1 | 1 | #REF! | 8 | #REF!
7.8 |  | HR | Doctor Kyat (LGC) Management Start team | Head of Accounting officially joined the team |  | Sai Hnin Aung | done | 0 |  | 2016-11-15 | 1 | 1 | #REF! | 8 | #REF!
7.9 |  | HR | Doctor Kyat (LGC) Management Start team | Recruit Head of Call Center - Job offer signed | Zin Mar Htwe | July Phoo | done | 5 |  | 2016-11-20 | 1 | 1 | #REF! | 8 | #REF!
7.10 |  | HR | Doctor Kyat (LGC) Management Start team | Head of Call Center officially joined the team |  | July Phoo | done | 0 |  |  | 1 | 1 | #REF! | 8 | #REF!
7.11 |  | HR | Doctor Kyat (LGC) Mass Start team | 2 Outbound Sales operators officially joined the team | Hnin Wai, Yu Yu | July Phoo | done | 25 |  | 2016-09-01 | 1 | 1 | #REF! | 8 | #REF!
7.12 |  | HR | Doctor Kyat (LGC) Mass Start team | 2 Customer Support operators officially joined the team |  | July Phoo | in progress | 25 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
7.13 |  | HR | Doctor Kyat (LGC) Mass Start team | 2 Inbound Sales operators officially joined the team | Chaw Hsu Hsu Thant, Zin Phyo Thu | July Phoo | done | 25 |  | 2016-11-19 | 1 | 1 | #REF! | 8 | #REF!
7.14 |  | HR | LAT Mass Start team | 2 Phone Verifiers officially joined the team | Htet Aung Kyaw, Aeint Aeint Thu | July Phoo | done | 25 |  | 2016-09-01 | 1 | 1 | #REF! | 8 | #REF!
7.15 |  | HR | Doctor Kyat (LGC) Management Start team | Recruit Head of HR - Job offer signed | Aung Pyay Thein | Sai Hnin Aung | done | 20 | #REF! | 2016-11-18 | 1 | 1 | #REF! | 8 | #REF!
7.16 |  | HR | Doctor Kyat (LGC) Management Start team | Head of HR officially joined the team |  | Sai Hnin Aung | done | 0 | #REF! | 2016-11-24 | 1 | 1 | #REF! | 8 | #REF!
7.17 |  | HR | LAT Management Start team | Recruit СOО - Job offer signed | July Phoo | Sai Hnin Aung | done | 3 | 2016-11-04 | 2016-11-11 | 1 | 1 | #REF! | 8 | #REF!
7.18 |  | HR | LAT Management Start team | СOО joined the team |  | Sai Hnin Aung | done | 0 |  | 2016-11-11 | 1 | 1 | #REF! | 8 | #REF!
7.19 |  | HR | LAT Management Start team | Recruit IT Manager - Job offer signed | Kyaw Swe Myint | Dziatkovskiy | done | 15 | #REF! | 2016-11-18 | 1 | 1 | #REF! | 8 | #REF!
7.20 |  | HR | LAT Management Start team | IT Manager officially joined the team |  | Dziatkovskiy | in progress | 0 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
9 |  | Legal |  | Customer & Entities Legal agreements are drafted | [8 empty] | #REF! | #REF!
9.1 |  | Legal | Legal entities relations | Service contract between Pawnshop & LGC (entities relations) is drafted |  | Head of legal | in progress | 14 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
9.2 |  | Legal | Customer docs | Loan Agreement with Pawnshop bilingual (Customer docs) is drafted |  | Head of legal | in progress | 14 | 2016-10-27 |  | 1 | 0.5 | #REF! | #REF! | #REF!
9.3 |  | Legal | Customer docs | Service agreement with LGC bilingual(Customer docs) is drafted |  | Head of legal | in progress | 14 | 2016-10-27 |  | 1 | 0.5 | #REF! | #REF! | #REF!
9.4 |  | Legal | Customer docs | Welcome letter (Customer docs) is drafted |  | Head of legal | Done | 5 | 2016-10-27 | 2016-11-28 | 1 | 1 | #REF! | 8 | #REF!
9.5 |  | Legal | Customer docs | Tariffs (Customer docs) are drafted |  | Head of legal | done | 5 | 2016-10-27 | 2016-11-28 | 1 | 1 | #REF! | 8 | #REF!
10 |  | Marketing |  | User-friendly design for customer docs is created | [8 empty] | #REF! | #REF!
10.1 |  | Marketing | User-friendly design for customer docs is created | proper design for Loan Agreement is created |  | Dziatkovskiy | in progress | 5 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
10.2 |  | Marketing | User-friendly design for customer docs is created | proper design for Service Agreement is created |  | Dziatkovskiy | in progress | 5 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
10.3 |  | Marketing | User-friendly design for customer docs is created | Welcome letter as an email template is created |  | Dziatkovskiy | done | 5 |  | 2016-11-28 | 1 | 1 | #REF! | 8 | #REF!
10.4 |  | Marketing | User-friendly design for customer docs is created | proper design for Tariffs are created |  | Dziatkovskiy | in progress | 5 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
10.5 |  | Marketing | User-friendly design for customer docs is created | to design Email content considering printing form |  | Dziatkovskiy | done | 10 | 2016-10-28 | 2016-11-28 | 1 | 1 | #REF! | 8 | #REF!
11 |  | Operations |  | Office Renovation is finished | [8 empty] | #REF! | 8
11.1 |  | Operations | Office Renovation | Lease agreement is signed | Lease agreement | Dziatkovskiy | done | 7 | 2016-10-27 | 2016-10-01 | 1 | 1 | #REF! | 8 | #REF!
11.2 |  | Operations | Office Renovation | Cabling (2 powers sockets& 1LAN per WS) is done | Specifications | IT manager | done | 7 | 2016-10-28 | 2016-11-07 | 1 | 1 | #REF! | 8 | #REF!
11.4 |  | Operations | Office Renovation | Partitioning (Renovation if required) is done |  | Sai Hnin Aung | done | 14 | 2016-10-28 | 2016-11-07 | 1 | 1 | #REF! | 8 | #REF!
11.5 |  | Operations | Office Renovation | Communications (cables electricity, CCTV, internet cables) is arranged |  | IT manager | done | 7 | 2016-10-28 | 2016-11-25 | 1 | 1 | #REF! | 8 | #REF!
11.6 |  | Operations | Office Renovation | Office furniture is set |  | IT manager | done | 14 | 2016-10-28 | 2016-11-25 | 1 | 1 | #REF! | 8 | #REF!
12 |  | IT |  | Office Infrastructure is set | [8 empty] | #REF! | #REF!
12.1 |  | IT | Office Infrastructure development | Office equipment (computers + org technics). Quotation is received |  | Sai Hnin Aung | done | 5 | #REF! | 2016-11-25 | 1 | 1 | #REF! | 8 | #REF!
12.2 |  | IT | Office Infrastructure development | Office equipment (computers + org technics) Quotation is approved |  | Sai Hnin Aung | done | 3 |  | 2016-11-28 | 1 | 1 | #REF! | 8 | #REF!
12.3 |  | IT | Office Infrastructure development | Office equipment (computers + org technics) payd and delivered |  | Sai Hnin Aung | in progress | 14 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
12.4 |  | IT | Office Infrastructure development | Office equipment (computers + org technics) deployed |  | Sai Hnin Aung | not started | 3 |  |  | 1 | 0 | #REF! | #REF! | #REF!
12.5 |  | IT | Office Infrastructure development | Landline phonelines. Quotations is received |  | Dziatkovskiy | done | 3 | 2016-10-24 | 2016-10-27 | 1 | 1 | #REF! | 8 | #REF!
12.6 |  | IT | Office Infrastructure development | Landline phonelines. Operator is chosen |  | Dziatkovskiy | done | 3 | #REF! | #REF! | 1 | 1 | #REF! | 8 | #REF!
12.7 |  | IT | Office Infrastructure development | Landline phonelines. Contract is signed |  | Dziatkovskiy | done | 7 | 2016-11-02 | 2016-11-15 | 1 | 1 | #REF! | 8 | #REF!
12.8 |  | IT | Office Infrastructure development | Landline phonelines. Delivered |  | Dziatkovskiy | in progress | 7 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
12.9 |  | IT | Office Infrastructure development | Landline phonelines Test the phone on hunting line, inbound & outbound call |  | IT manager | not started | 2 |  |  | 1 | 0 | #REF! | #REF! | #REF!
12.10 |  | IT | Office Infrastructure development | Landline phonelines Deployed |  | IT manager | not started | 1 |  |  | 1 | 0 | #REF! | #REF! | #REF!
12.11 |  | IT | Office Infrastructure development | Internet. Quotations is received | Internet leased circuit | Dziatkovskiy | done | 3 | 2016-10-24 | 2016-10-27 | 1 | 1 | #REF! | 8 | #REF!
12.12 |  | IT | Office Infrastructure development | Internet. Vendor is chosen | Dialog Axiata | Dziatkovskiy | done | 1 | 2016-11-02 | 2016-11-03 | 1 | 1 | #REF! | 8 | #REF!
12.13 |  | IT | Office Infrastructure development | Internet. Contract is signed |  | Dziatkovskiy | done | 7 | 2016-11-03 | 2016-11-07 | 1 | 1 | #REF! | 8 | #REF!
12.14 |  | IT | Office Infrastructure development | Internet. Vendor to setup Internet line |  | IT manager | done | 14 |  | 2016-11-07 | 1 | 1 | #REF! | 8 | #REF!
12.15 |  | IT | Office Infrastructure development | Internet. UAT deployed |  | IT manager | done | 2 |  | 2016-11-07 | 1 | 1 | #REF! | 8 | #REF!
12.16 |  | IT | Office Infrastructure development | Internet. Deployed |  | IT manager | done | 1 |  | 2016-11-07 | 1 | 1 | #REF! | 8 | #REF!
12.17 |  | IT | Office Infrastructure development | Staff move |  | Dziatkovskiy | done | 0 |  | 2016-11-07 | 1 | 1 | #REF! | 8 | #REF!
12.18 |  | IT | Office Infrastructure development | UAT Test for CCTV |  | IT manager | not started | 3 |  |  | 1 | 0 | #REF! | #REF! | #REF!
12.19 |  | IT | Office Infrastructure development | UAT Test for Access System |  | IT manager | not started | 3 |  |  | 1 | 0 | #REF! | #REF! | #REF!
13 |  | IT |  | Initial IT infrastructure (SMS gateway, Data center) is set | [8 empty] | #REF! | #REF!
13.1 |  | IT | SMS gateway provider | Sms provider. Contract is received | Customer agreement - TextWare | Dziatkovskiy | done | 7 | 2016-10-17 | 2016-10-17 | 1 | 1 | #REF! | 8 | #REF!
13.2 |  | IT | SMS gateway provider | Sms provider. Contract is approved (Legal, CM, PS) |  | Dziatkovskiy | done | 5 | 2016-11-07 |  | 1 | 1 | #REF! | 8 | #REF!
13.3 |  | IT | SMS gateway provider | Sms provider. Contract is signed |  | Dziatkovskiy | done | 2 |  |  | 1 | 1 | #REF! | 8 | #REF!
13.4 |  | IT | SMS gateway provider | Sms provider. API information is provided to TS |  | Dziatkovskiy | done | 1 | 2016-11-03 | 2016-11-04 | 1 | 1 | #REF! | 8 | #REF!
13.5 |  | IT | SMS gateway provider | Sms provider. Integration is done |  | Dziatkovskiy | in progress | 10 | 2016-11-05 |  | 1 | 0.5 | #REF! | #REF! | #REF!
13.6 |  | IT | SMS gateway provider | Sms provider. UAT Test done |  | IT manager | in progress | 3 | 2016-11-05 |  | 1 | 0.5 | #REF! | #REF! | #REF!
13.7 |  | IT | SMS gateway provider | Sms provider. Deployed |  | IT manager | not started | 3 |  |  | 1 | 0 | #REF! | #REF! | #REF!
13.8 |  | IT | Telephony | Server for GSM gateway. Quotation is received and paid |  |  | in progress | 3 | 2016-11-15 |  | 1 | 0.5 | #REF! | #REF! | #REF!
13.9 |  | IT | Telephony | Server for GSM gateway. Deployed |  |  | in progress |  |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
13.10 |  | IT | Telephony | GSM gateway. Quotation is received and paid |  |  | done | 3 | 2016-11-15 | 2016-11-25 | 1 | 1 | #REF! | 8 | #REF!
13.11 |  | IT | Telephony | GSM gateway. Deployed | [6 empty] | 1 | 0 | #REF! | #REF! | #REF!
13.12 |  | IT | Data Center provider | Data center for Telephony + TS. Contract is received |  | Dziatkovskiy | not started | 7 |  |  | 1 | 0 | #REF! | #REF! | #REF!
13.13 |  | IT | Data Center provider | Data center for Telephony + TS. Contract is approved (Legal, CM, PS) |  | Dziatkovskiy | not started | 10 |  |  | 1 | 0 | #REF! | #REF! | #REF!
13.14 |  | IT | Data Center provider | Data center for Telephony + TS. Contract is signed |  | Dziatkovskiy | not started | 2 |  |  | 1 | 0 | #REF! | #REF! | #REF!
13.15 |  | IT | Data Center provider | Data center for Telephony + TS. Communication is established |  | IT manager | not started | 5 |  |  | 1 | 0 | #REF! | #REF! | #REF!
13.16 |  | IT | Data Center provider | Data center for Telephony + TS. UAT Test done |  | IT manager | not started | 2 |  |  | 1 | 0 | #REF! | #REF! | #REF!
13.17 |  | IT | Data Center provider | Data center for Telephony + TS. Production Deployment is done |  | IT manager | not started | 3 |  |  | 1 | 0 | #REF! | #REF! | #REF!
14 |  | Finance |  | Ad-hoc payments are provided (lease, equipment, Internet, SMS, DC) | [8 empty] | #REF! | #REF!
14.1 |  | Finance | Ad-hoc payments | Advanced payment for the office is done | Invoice | Dziatkovskiy | done | 1 | 2016-10-28 | 2016-10-28 | 1 | 1 | #REF! | 8 | #REF!
14.2 |  | Finance | Ad-hoc payments | Office equipment (computers + org technics) is paid |  | Sai Hnin Aung | in progress | 3 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
14.3 |  | Finance | Ad-hoc payments | Landline phonelines is paid |  | Dziatkovskiy | in progress | 3 | 2016-11-09 |  | 1 | 0.5 | #REF! | #REF! | #REF!
14.4 |  | Finance | Ad-hoc payments | Advance payment for the Internet is paid (setup is free, no advance payment required) |  | Dziatkovskiy | in progress | 3 | #REF! |  | 1 | 0.5 | #REF! | #REF! | #REF!
14.5 |  | Finance | Ad-hoc payments | Upfront payment to Sms provider for gateway setup is done |  | Dziatkovskiy | in progress | 3 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
14.6 |  | Finance | Ad-hoc payments | Payment for GSM gateway for telephony is done |  | Dziatkovskiy | in progress | 3 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
15 |  | IT |  | Website is developed | [8 empty] | #REF! | #REF!
15.1 |  | IT | Website development | Domain is registered (if needed) | www.doctorkyat.com.mm | Dziatkovskiy | done | 5 | 2016-10-27 | 2016-11-04 | 1 | 1 | #REF! | 8 | #REF!
15.2 |  | IT | Website development | json format in XLS is created (web transfer json format to TS with actual codes) | JSON | Dziatkovskiy | done | 5 | 2016-10-12 | 2016-10-17 | 1 | 1 | #REF! | 8 | #REF!
15.3 |  | IT | Website development | Website concept is developed | Site concept | Dziatkovskiy | done | 7 | 2016-10-25 | 2016-10-31 | 1 | 1 | #REF! | 8 | #REF!
15.4 |  | IT | Website development | Website concept is approved by RH (Alex Isaev, Dima Eg) |  | Dziatkovskiy | done | 6 | 2016-11-01 | 2016-11-07 | 1 | 1 | #REF! | 8 | #REF!
15.5 |  | IT | Website development | Website is developed (First Content) |  | Dziatkovskiy | in progress | 14 | #REF! |  | 1 | 0.5 | #REF! | #REF! | #REF!
15.6 |  | IT | Website development | Test the operation of the website |  | Head of Dig Marketing | not started | 5 |  |  | 1 | 0 | #REF! | #REF! | #REF!
15.7 |  | IT | Website development | Website is ready |  | Head of Dig Marketing | not started | 0 |  |  | 1 | 0 | #REF! | #REF! | #REF!
16 |  | Digital Sales |  | Media plan is prepared | [8 empty] | #REF! | #REF!
17.1 |  | Digital Sales | Media plan | Website in Google Analytics is registered |  | Head of Dig Marketing | not started | 3 |  |  | 1 | 0 | #REF! | #REF! | #REF!
17.2 |  | Digital Sales | Media plan | Payment corp card is issued |  | Sai Hnin Aung | done | 15 |  | 2016-09-01 | 1 | 1 | #REF! | 8 | #REF!
17.3 |  | Digital Sales | Media plan | Corp card linked to FB, Google account |  | Head of Marketing | done | 2 |  | 2016-09-01 | 1 | 1 | #REF! | 8 | #REF!
17.4 |  | Digital Sales | Media plan | Dmitry provides the keywords & the banners examples |  | Head of Marketing | done | 3 |  | 2016-09-01 | 1 | 1 | #REF! | 8 | #REF!
17.5 |  | Digital Sales | Media plan | Keywords is adopted |  | Head of Marketing | done | 4 |  | 2016-09-01 | 1 | 1 | #REF! | 8 | #REF!
17.6 |  | Digital Sales | Media plan | Budget for FaceBook and Google campaigns is approved |  | Head of Marketing | not started | 3 |  |  | 1 | 0 | #REF! | #REF! | #REF!
17 |  | Marketing |  | Media content (banners, campaings, etc.) is developed | [8 empty] | #REF! | #REF!
16.1 |  | Marketing | Media content | Messages for the banners is created |  | Head of Marketing | done | 3 |  |  | 1 | 1 | #REF! | 8 | #REF!
16.2 |  | Marketing | Media content | Banners are developed |  | Head of Marketing | not started | 7 |  |  | 1 | 0 | #REF! | #REF! | #REF!
16.3 |  | Marketing | Media content | Face Book campaign is created |  | Head of Marketing | not started | 3 |  |  | 1 | 0 | #REF! | #REF! | #REF!
16.4 |  | Marketing | Media content | Google campaign is created |  | Head of Marketing | not started | 3 |  |  | 1 | 0 | #REF! | #REF! | #REF!
18 |  | Digital Sales |  | Social media presence is set up | [8 empty] | #REF! | #REF!
18.1 |  | Digital Sales | Social Media | FaceBook fanpage + Content in English is done |  | Head of Marketing | in progress | 3 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
18.2 |  | Digital Sales | Social Media | FaceBook fanpage Content + Site texts in Burmese is done |  | Head of Marketing | in progress | 3 |  |  | 1 | 0.5 | #REF! | #REF! | #REF!
18.3 |  | Digital Sales | Social Media | Budget for Social media (fanpages) is approved |  | Head of Marketing | not started | 2 |  |  | 1 | 0 | #REF! | #REF! | #REF!
19 |  | IT |  | Terrasoft Software is customized for local market | [8 empty] | #REF! | #REF!
19.1 |  | IT | Software Customization | Terrasoft CRM is customized (details in IT project plan) |  | Dziatkovskiy | in progress | 55 | 2016-10-25 |  | 1 | 0.5 | #REF! | #REF! | #REF!
[11 empty] | 133 | 91.5

## Launch plan - Phase 2
| End of Phase 1 (First loan to be disbursed) |  |  | 2016-12-15 | Launch plan - Phase 2
| End of Phase 2 (Operations are set, 100 loans disbursed) |  |  | 2017-02-01
Progress
№ | Company |  | Sub line | Task | Document/ Link | Responsible MM | Status | Duration, days | Start plan | Start fact | Finish plan | Finish fact |  | 0% |  | Task Status | Days to the end of Phase 1
20 |  | HR |  | Initial Collection team is hired |  |  |  |  | 2016-11-18 |  | 2017-01-27 |  |  |  | 0 | 0
20.1 |  | HR | Initial Collection team | Recruit Head of Collection - Job offer signed |  | Sai Hnin Aung | not started | 20 | 2016-11-18 |  | 2016-12-08 |  | 1 | 0 | 0 | 0 | 55
20.2 |  | HR | Initial Collection team | Head of Collection officially joined the team |  | Sai Hnin Aung | not started | 0 | 2017-01-07 |  | 2017-01-07 |  | 1 | 0 | 0 | 0 | 25
20.3 |  | HR | Initial Collection team | 2 Soft Collectors officially joined the team |  | Sai Hnin Aung | not started | 10 | 2017-01-07 |  | 2017-01-17 |  | 1 | 0 | 0 | 0 | 15
20.4 |  | HR | Initial Collection team | 2 Hard Collectors officially joined the team |  | Sai Hnin Aung | not started | 10 | 2017-01-17 |  | 2017-01-27 |  | 1 | 0 | 0 | 0 | 5
21 |  | HR |  | Staff management standards are implemented |  |  |  |  | #REF! |  | #REF! |  |  |  | #REF! | #REF!
21.1 |  | HR | Staff management standards | the procedure for hiring employees is drafted |  | Head of HR | not started | 10 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
21.2 |  | HR | Staff management standards | the procedure for firing employees is drafted |  | Head of HR | not started | 10 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
21.3 |  | HR | Staff management standards | Corporate standards (sick leave, compensatory leave, annual leave) is created |  | Head of HR | not started | 14 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
21.4 |  | HR | Staff management standards | Corporate standards (dress code, working time, sick leave, compensatory leave, leave) is created |  | Head of HR | not started | 10 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
21.5 |  | HR | Staff management standards | Orientation Program is created |  | Head of HR | not started | 7 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
21.6 |  | HR | Staff management standards | The procedure for registration of employees in the system and lock systems is created |  | Head of HR | not started | 10 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
22 |  | HR |  | Mass team recruitment and training is arranged |  |  |  |  | #REF! |  | #REF! |  |  |  | #REF! | #REF!
22.1 |  | HR | Mass team recruitment and training | Call Center - Calendar plan of recruitment and training is made |  | Head of Call Center | not started | 5 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
22.2 |  | HR | Mass team recruitment and training | Team of Call Center is recruited |  | Head of Call Center | not started | 20 | 2016-12-05 |  | 2016-12-25 |  | 1 | 0 | 0 | 0 | 38
22.3 |  | HR | Mass team recruitment and training | PH verifiers - Calendar plan of recruitment and training is made |  | Sai Hnin Aung | not started | 5 | 2016-12-05 |  | 2016-12-10 |  | 1 | 0 | 0 | 0 | 53
22.4 |  | HR | Mass team recruitment and training | Team of Phone verifiers is recruited |  | Sai Hnin Aung | not started | 20 | 2016-12-10 |  | 2016-12-30 |  | 1 | 0 | 0 | 0 | 33
22.5 |  | HR | Mass team recruitment and training | Collection - Calendar plan of recruitment and training is made |  | Head of Collection | not started | 5 | 2017-01-07 |  | 2017-01-12 |  | 1 | 0 | 0 | 0 | 20
22.6 |  | HR | Mass team recruitment and training | Team for collection is recruited |  | Head of Collection | not started | 20 | 2017-01-12 |  | 2017-02-01 |  | 1 | 0 | 0 | 0 | 0
23 |  | Digital Sales |  | Reports & Analytics are set up |  |  |  |  | 2016-12-15 |  | 2016-12-24 |  |  |  | 0 | 0
23.1 |  | Digital Sales | Reports & Analitics | Daily Sales funnel template is made |  | Head of Marketing | not started | 5 | 2016-12-15 |  | 2016-12-20 |  | 1 | 0 | 0 | 0 | 43
23.2 |  | Digital Sales | Reports & Analitics | Install Google Tag Manager |  | Head of Marketing | not started | 5 | 2016-12-16 |  | 2016-12-21 |  | 1 | 0 | 0 | 0 | 42
23.3 |  | Digital Sales | Reports & Analitics | Install MouseStat |  | Head of Marketing | not started | 5 | 2016-12-17 |  | 2016-12-22 |  | 1 | 0 | 0 | 0 | 41
23.4 |  | Digital Sales | Reports & Analitics | Install Hotjar |  | Head of Marketing | not started | 5 | 2016-12-18 |  | 2016-12-23 |  | 1 | 0 | 0 | 0 | 40
23.5 |  | Digital Sales | Reports & Analitics | Install Google Analytics |  | Head of Marketing | not started | 5 | 2016-12-19 |  | 2016-12-24 |  | 1 | 0 | 0 | 0 | 39
23.6 |  | Digital Sales | Reports & Analitics | Start reports are created |  | Head of Marketing | not started | 0 | 2016-12-24 |  | 2016-12-24 |  | 1 | 0 | 0 | 0 | 39
24 |  | Operations |  | Call Center Team performance is handled |  |  |  |  | #REF! |  | #REF! |  |  |  | #REF! | #REF!
24.1 |  | Operations | CC Job descriptions | Job descriptions (operator, manager, assistant) are made |  | Head of Call Center | not started | 5 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.2 |  | Operations | CC KPI | KPI & Motivation scheme are developed |  | Head of Call Center | not started | 5 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.3 |  | Operations | CC Scripts | Customer Support Scripts (Routing tree) are created |  | Head of Call Center | not started | 7 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.4 |  | Operations | CC Scripts | Inbound Scripts are created |  | Head of Call Center | not started | 7 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.5 |  | Operations | CC Scripts | Script for working with objections are created |  | Head of Call Center | not started | 7 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.6 |  | Operations | CC Scripts | Call back scripts (outbound) are created |  | Head of Call Center | not started | 7 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.7 |  | Operations | CC Scripts | Prolongation scripts (outbound) are created |  | Head of Call Center | not started | 7 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.8 |  | Operations | CC Scripts | Repeat sales scripts (outbound) are created |  | Head of Call Center | not started | 7 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.9 |  | Operations | CC working schedule | Working schedule is arranged |  | Head of Call Center | not started | 5 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.10 |  | Operations | CC Instructions | Instruction for working in CRM is created |  | Head of Call Center | not started | 3 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.11 |  | Operations | CC Trainings | Training materials are created |  | Head of Call Center | not started | 5 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.12 |  | Operations | CC Trainings | Trainings are done |  | Head of Call Center | not started | 3 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.13 |  | Operations | CC Reports | Timesheets report is set-up |  | Head of Call Center | not started | 10 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.14 |  | Operations | CC Reports | % Of received and missed calls / Service level report is set-up |  | Head of Call Center | not started | 10 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.15 |  | Operations | CC Reports | Timing per call report is set-up |  | Head of Call Center | not started | 10 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.16 |  | Operations | CC Reports | Inbound: Calls to Applications report is set-up |  | Head of Call Center | not started | 10 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.17 |  | Operations | CC Reports | Inbound: Call back Sales Funnel Plan/Fact report is set-up |  | Head of Call Center | not started | 10 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.18 |  | Operations | CC Reports | Inbound: Rejection reasons report is set up |  | Head of Call Center | not started | 10 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.19 |  | Operations | CC Reports | Outbound: Load, plan / fact report is set-up |  | Head of Call Center | not started | 10 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.20 |  | Operations | CC Reports | Outbound: Repeat Sales Funnel, plan / fact report is set-up |  | Head of Call Center | not started | 10 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
24.22 |  | Operations | CC Reports | Outbound: Rejection reasons report is set-up |  | Head of Call Center | not started | 10 | #REF! |  | #REF! |  | 1 | 0 | #REF! | #REF! | #REF!
25 |  | Risk |  | Phone Verification Team performance is handled |  |  |  |  | 2016-12-01 |  | 2017-01-01 |  |  |  | 0 | 0
25.1 |  | Risk | Phone Verification Team | Job descriptions (operator, manager, assistant) are made |  | Sai Hnin Aung | not started | 5 | 2016-12-01 |  | 2016-12-06 |  | 1 | 0 | 0 | 0 | 57
25.2 |  | Risk | PHV KPI | KPI & Motivation scheme are developed |  | Sai Hnin Aung | not started | 5 | 2016-12-06 |  | 2016-12-11 |  | 1 | 0 | 0 | 0 | 52
25.3 |  | Risk | PHV Scripts | Verification Script is created |  | Sai Hnin Aung | not started | 5 | 2016-12-06 |  | 2016-12-11 |  | 1 | 0 | 0 | 0 | 52
25.4 |  | Risk | PHV Working schedule | Working schedule is arranged |  | Sai Hnin Aung | not started | 5 | 2016-12-06 |  | 2016-12-11 |  | 1 | 0 | 0 | 0 | 52
25.5 |  | Risk | PHV Instructions | Instruction for working in CRM is created |  | Sai Hnin Aung | not started | 3 | 2016-12-11 |  | 2016-12-14 |  | 1 | 0 | 0 | 0 | 49
25.6 |  | Risk | PHV Trainings | Training materials are created |  | Sai Hnin Aung | not started | 5 | 2016-12-14 |  | 2016-12-19 |  | 1 | 0 | 0 | 0 | 44
25.7 |  | Risk | PHV Trainings | Trainings are done |  | Sai Hnin Aung | not started | 3 | 2016-12-19 |  | 2016-12-22 |  | 1 | 0 | 0 | 0 | 41
25.8 |  | Risk | PHV Reports | Timesheets report is set-up |  | Sai Hnin Aung | not started | 10 | 2016-12-22 |  | 2017-01-01 |  | 1 | 0 | 0 | 0 | 31
25.9 |  | Risk | PHV Reports | Load, plan / fact report is set-up |  | Sai Hnin Aung | not started | 10 | 2016-12-22 |  | 2017-01-01 |  | 1 | 0 | 0 | 0 | 31
25.10 |  | Risk | PHV Reports | Funnel, plan / fact report is set-up |  | Sai Hnin Aung | not started | 10 | 2016-12-22 |  | 2017-01-01 |  | 1 | 0 | 0 | 0 | 31
25.11 |  | Risk | PHV Reports | Rejection reasons report is set-up |  | Sai Hnin Aung | not started | 10 | 2016-12-22 |  | 2017-01-01 |  | 1 | 0 | 0 | 0 | 31
25.12 |  | Risk | PHV Reports | Overdue report is set-up |  | Sai Hnin Aung | not started | 10 | 2016-12-22 |  | 2017-01-01 |  | 1 | 0 | 0 | 0 | 31
26 |  | Risk |  | Collection team performance is handled |  |  |  |  | 2017-01-12 |  | 2017-02-11 |  |  |  | 0 | 0
26.1 |  | Risk | Collection. Job descriptions | Job descriptions (operator, manager, assistant) are made |  | Head of Collection | not started | 5 | 2017-01-12 |  | 2017-01-17 |  | 1 | 0 | 0 | 0 | 15
26.2 |  | Risk | Collection. KPI | KPI & Motivation scheme are developed |  | Head of Collection | not started | 5 | 2017-01-17 |  | 2017-01-22 |  | 1 | 0 | 0 | 0 | 10
26.3 |  | Risk | Collection. Scripts | Soft Collection Scripts is created |  | Head of Collection | not started | 5 | 2017-01-17 |  | 2017-01-22 |  | 1 | 0 | 0 | 0 | 10
26.4 |  | Risk | Working Collection. schedule | Working schedule is arranged |  | Head of Collection | not started | 5 | 2017-01-17 |  | 2017-01-22 |  | 1 | 0 | 0 | 0 | 10
26.5 |  | Risk | Collection. Instructions | Instruction for working in CRM is created |  | Head of Collection | not started | 3 | 2017-01-22 |  | 2017-01-25 |  | 1 | 0 | 0 | 0 | 7
26.6 |  | Risk | Collection. Training | Training materials are created |  | Head of Collection | not started | 5 | 2017-01-25 |  | 2017-01-30 |  | 1 | 0 | 0 | 0 | 2
26.7 |  | Risk | Collection. Trainings | Trainings are done |  | Head of Collection | not started | 2 | 2017-01-30 |  | 2017-02-01 |  | 1 | 0 | 0 | 0 | 0
26.8 |  | Risk | Collection. Procedure | Field Collection Procedure is created |  | Head of Collection | not started | 10 | 2017-02-01 |  | 2017-02-11 |  | 1 | 0 | 0 | 0 | -10
26.9 |  | Risk | Collection. Reports | Timesheets report is set-up |  | Head of Collection | not started | 10 | 2017-02-01 |  | 2017-02-11 |  | 1 | 0 | 0 | 0 | -10
26.10 |  | Risk | Collection. Reports | Load, plan / fact report is set-up |  | Head of Collection | not started | 10 | 2017-02-01 |  | 2017-02-11 |  | 1 | 0 | 0 | 0 | -10
26.11 |  | Risk | Collection. Reports | Soft Collection Funnel, plan / fact report is set-up |  | Head of Collection | not started | 10 | 2017-02-01 |  | 2017-02-11 |  | 1 | 0 | 0 | 0 | -10
26.12 |  | Risk | Collection. Reports | Hard Collection Funnel, plan / fact report is set-up |  | Head of Collection | not started | 10 | 2017-02-01 |  | 2017-02-11 |  | 1 | 0 | 0 | 0 | -10
27 |  | Finance |  | Agreement with General Ledger is signed |  |  |  |  | 2016-12-18 |  | 2017-01-02 |  |  |  | 0 | 0
27.1 |  | Finance | General Ledger implementation | General Ledger (GL) Auto Count-Contract for LGC received |  | Chief accountant | not started | 10 | 2016-12-18 |  | 2016-12-28 |  | 1 | 0 | 0 | 0 | 35
27.2 |  | Finance | General Ledger implementation | General Ledger (GL) Auto Count-Contract for LGC signed |  | Chief accountant | not started | 5 | 2016-12-28 |  | 2017-01-02 |  | 1 | 0 | 0 | 0 | 30
27.3 |  | Finance | General Ledger implementation | General Ledger (GL) Auto Count for MAT - Contract received |  | Chief accountant | not started | 10 | 2016-12-18 |  | 2016-12-28 |  | 1 | 0 | 0 | 0 | 35
27.4 |  | Finance | General Ledger implementation | General Ledger (GL) Auto Count for MAT - Contract sign |  | Chief accountant | not started | 5 | 2016-12-28 |  | 2017-01-02 |  | 1 | 0 | 0 | 0 | 30
28 |  | HR |  | Agreement with Payroll agent is signed |  |  |  |  | 2016-12-15 |  | 2016-12-27 |  |  |  | 0 | 0
28.1 |  | HR | Payroll & HR | Payroll Quotation for LGC Received |  | Chief accountant | not started | 7 | 2016-12-15 |  | 2016-12-22 |  | 1 | 0 | 0 | 0 | 41
28.2 |  | HR | Payroll & HR | Payroll Contract for LGC signed |  | Chief accountant | not started | 5 | 2016-12-22 |  | 2016-12-27 |  | 1 | 0 | 0 | 0 | 36
29 |  | Operations |  | Agreements with disbursement & repayment agents are signed |  |  |  |  | 2016-12-15 |  | 2017-01-20 |  |  |  | 0 | 0
29.1 |  | Operations | Agreement with disbursement & repayment agents | Disbursement Agent - Contract received |  | Sai Hnin Aung | not started | 7 | 2016-12-15 |  | 2016-12-22 |  | 1 | 0 | 0 | 0 | 41
29.2 |  | Operations | Agreement with disbursement & repayment agents | Disbursement Agent - Sign Contract done |  | Sai Hnin Aung | not started | 5 | 2016-12-22 |  | 2016-12-27 |  | 1 | 0 | 0 | 0 | 36
29.3 |  | Operations | Agreement with disbursement & repayment agents | Repayment Agent Sign Contract Received |  | Sai Hnin Aung | not started | 10 | 2017-01-05 |  | 2017-01-15 |  | 1 | 0 | 0 | 0 | 17
29.4 |  | Operations | Agreement with disbursement & repayment agents | Repayment Agent Sign Contract Done |  | Sai Hnin Aung | not started | 5 | 2017-01-15 |  | 2017-01-20 |  | 1 | 0 | 0 | 0 | 12
30 |  | IT |  | IT infrastructure is completed |  |  |  |  | 0 |  | 2017-01-30 |  |  |  | 0 | 0
30.1 |  | IT | IT infrastructure | General Ledger (GL) Auto Count for (LGC). API detail passed to TS |  | Chief accountant | not started | 2 | 2017-01-02 |  | 2017-01-04 |  | 1 | 0 | 0 | 0 | 28
30.2 |  | IT | IT infrastructure | General Ledger (GL) Auto Count for (LGC). Api integration done with TS |  | Chief accountant | not started | 10 | 2017-01-04 |  | 2017-01-14 |  | 1 | 0 | 0 | 0 | 18
30.3 |  | IT | IT infrastructure | General Ledger (GL) Auto Count for (LGC). UAT Test done |  | Chief accountant | not started | 2 | 2017-01-14 |  | 2017-01-16 |  | 1 | 0 | 0 | 0 | 16
30.4 |  | IT | IT infrastructure | General Ledger (GL) Auto Count for (LGC) Production deployment done |  | Chief accountant | not started | 2 | 2017-01-16 |  | 2017-01-18 |  | 1 | 0 | 0 | 0 | 14
30.5 |  | IT | IT infrastructure | General Ledger (GL) Auto Count for MAT. API detail passed to TS |  | Chief accountant | not started | 2 | 2017-01-02 |  | 2017-01-04 |  | 1 | 0 | 0 | 0 | 28
30.6 |  | IT | IT infrastructure | General Ledger (GL) Auto Count for MAT. Api integration done with TS |  | Chief accountant | not started | 10 | 2017-01-04 |  | 2017-01-14 |  | 1 | 0 | 0 | 0 | 18
30.7 |  | IT | IT infrastructure | General Ledger (GL) Auto Count for MAT. UAT Test done |  | Chief accountant | not started | 2 | 2017-01-14 |  | 2017-01-16 |  | 1 | 0 | 0 | 0 | 16
30.8 |  | IT | IT infrastructure | General Ledger (GL) Auto Count Production for MAT deployment done |  | Chief accountant | not started | 2 | 2017-01-16 |  | 2017-01-18 |  | 1 | 0 | 0 | 0 | 14
30.9 |  | IT | IT infrastructure | Payroll Contract for (LGC) - UAT Test done |  | Chief accountant | not started | 2 | 2016-12-29 |  | 2016-12-31 |  | 1 | 0 | 0 | 0 | 32
30.10 |  | IT | IT infrastructure | Payroll Contract for (LGC) - Deployed done |  | Chief accountant | not started | 10 | 2016-12-31 |  | 2017-01-10 |  | 1 | 0 | 0 | 0 | 22
30.11 |  | IT | IT infrastructure | Payroll Contract for MAT - UAT Test done |  | Chief accountant | not started | 2 | 2016-01-17 |  | 2016-01-19 |  | 1 | 0 | 0 | 0 | 379
30.12 |  | IT | IT infrastructure | Payroll Contract for MAT Deployed done |  | Chief accountant | not started | 10 | 2016-01-19 |  | 2016-01-29 |  | 1 | 0 | 0 | 0 | 369
30.13 |  | IT | IT infrastructure | Disbursement Agent Update in AC Account Done |  | Sai Hnin Aung | not started | 2 | 0 |  | 1900-01-01 |  | 1 | 0 | 0 | 0 | 42765
30.14 |  | IT | IT infrastructure | Disbursement Agent Production deployment done |  | Sai Hnin Aung | not started | 10 | 1900-01-01 |  | 1900-01-11 |  | 1 | 0 | 0 | 0 | 42755
30.15 |  | IT | IT infrastructure | Repayment Agent Production deployment done |  | Sai Hnin Aung | not started | 10 | 2017-01-20 |  | 2017-01-30 |  | 1 | 0 | 0 | 0 | 2
31 |  | Finance |  | Payments for IT infrastructure is made |  |  |  |  | 2016-01-15 |  | 2017-01-07 |  |  |  | 0 | 0
31.1 |  | Finance | Payments for IT infrastructure | General Ledger (GL) Auto Count for DR - Payment done |  | Chief accountant | not started | 5 | 2017-01-02 |  | 2017-01-07 |  | 1 | 0 | 0 | 0 | 25
31.2 |  | Finance | Payments for IT infrastructure | General Ledger (GL) Auto Count for LAT - Payment done |  | Chief accountant | not started | 5 | 2017-01-02 |  | 2017-01-07 |  | 1 | 0 | 0 | 0 | 25
31.3 |  | Finance | Payments for IT infrastructure | Payroll Contract payment done |  | Chief accountant | not started | 2 | 2016-12-27 |  | 2016-12-29 |  | 1 | 0 | 0 | 0 | 34
31.4 |  | Finance | Payments for IT infrastructure | Payroll Contract payment done |  | Chief accountant | not started | 2 | 2016-01-15 |  | 2016-01-17 |  | 1 | 0 | 0 | 0 | 381
[13 empty] | 96 | 0

## Headcount Funnel (hidden)
|  |  |  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1
|  |  |  | 2016-10-24 | 2016-10-25 | 2016-10-26 | 2016-10-27 | 2016-10-28 | 2016-10-31 | 2016-11-01 | 2016-11-02 | 2016-11-03 | 2016-11-04 | 2016-11-07 | 2016-11-08 | 2016-11-09 | 2016-11-10 | 2016-11-11 | 2016-11-14 | 2016-11-15 | 2016-11-16 | 2016-11-17 | 2016-11-18 | 2016-11-21
Manager |  | Head of Digitl Marketing
Manager | Head of Call Centre | CV |  | 2016-10-24: 10
Manager | Head of Call Centre | Interviews offered |  | 2016-10-24: 5
Manager | Head of Call Centre | Interviews done |  | 2016-10-25: 5
Manager | Head of Call Centre | Assessment | bar: 2016-10-31
Manager | Head of Call Centre | Offers
Manager | Head of Call Centre | Start
Manager |  | Head of Legal and Complience
Manager | Head of Operations | CV |  | 2016-10-26: 7
Manager | Head of Operations | Interviews offered |  | 2016-10-27: 2
Manager | Head of Operations | Interviews done
Manager | Head of Operations | Assessment
Manager | Head of Operations | Offers
Manager | Head of Operations | Start
Manager |  | Head of HR
Manager | Head of HR | CV |  | 2016-10-27: 28
Manager | Head of HR | Interviews offered |  | 2016-10-28: 4
Manager | Head of HR | Interviews done
Manager | Head of HR | Assessment
Manager | Head of HR | Offers
Manager | Head of HR | Start
Manager |  | Head of Accounting
Manager | Head of Logistics | CV |  | 2016-10-28: 14
Manager | Head of Logistics | Interviews offered
Manager | Head of Logistics | Interviews done
Manager | Head of Logistics | Assessment
Manager | Head of Logistics | Offers
Manager | Head of Logistics | Start
Manager |  | IT Manager
Manager | Head of Collection | CV |  | 2016-10-26: 24
Manager | Head of Collection | Interviews offered |  | 2016-10-27: 4; 2016-10-31: 1
Manager | Head of Collection | Interviews done |  | 2016-10-28: 2
Manager | Head of Collection | Assessment
Manager | Head of Collection | Offers
Manager | Head of Collection | Start
Manager |  | Head Of Call Centre
Manager | Head Of Marketing | CV
Manager | Head Of Marketing | Interviews offered
Manager | Head Of Marketing | Interviews done
Manager | Head Of Marketing | Assessment
Manager | Head Of Marketing | Offers
Manager | Head Of Marketing | Start
Manager |  | Head of Collection
Manager | Business Analyst | CV
Manager | Business Analyst | Interviews offered
Manager | Business Analyst | Interviews done
Manager | Business Analyst | Assessment
Manager | Business Analyst | Offers
Manager | Business Analyst | Start
Mass |  | Call Center
Mass | Call Center Customer Service | CV
Mass | Call Center Customer Service | Assessment offered
Mass | Call Center Customer Service | Trainings + materials done | 50%
Mass | Call Center Customer Service | Tests provided | 66%
Mass | Call Center Customer Service | Tests done | 70%
Mass | Call Center Customer Service | Start
Mass |  | Soft collectors
Mass | Data Checkers | CV
Mass | Data Checkers | Assessment offered
Mass | Data Checkers | Trainings + materials done
Mass | Data Checkers | Tests provided
Mass | Data Checkers | Tests done
Mass | Data Checkers | Start
Mass |  | Phone Verificators
Mass | Phone Verificators | CV
Mass | Phone Verificators | Assessment offered
Mass | Phone Verificators | Trainings + materials done
Mass | Phone Verificators | Tests provided
Mass | Phone Verificators | Tests done
Mass | Phone Verificators | Start

## KPI (hidden)
Inbound | Calls
Calls missed
total
by hours
Timing per call
Call back Sales Funnel Plan/Fact
Customer reached
Calls to Applications
Rejection reasons

## Launch team (hidden)
DR | DR Start team | Manager | Head of HR Section | LAT | LAT Start team | Manager | СOО, including Risk Analyse functions | Done
DR | DR Start team | Manager | Head of Legal | LAT | LAT Start team | Manager | Head Of phone verification (Head of Section)
DR | DR Start team | Manager | Head of Marketing | LAT | LAT Start team | Mass | Phone Verificator
DR | DR Start team | Manager | Marketing manager | LAT | LAT Start team | Mass | Phone Verificator
DR | DR Start team | Manager | Head of Accounting | LAT | LAT Start team | Mass | Phone Verificator
DR | DR Start team | Manager | Disbursement&repayment manager | LAT | LAT Start team | Mass | Phone Verificator
DR | DR Start team | Manager | Accountant | LAT | LAT Start team | Manager | Head of Collection Dept
DR | DR Start team | Manager | Head of Call Center | LAT | LAT Start team | Mass | Soft Collector
DR | DR Start team | Mass | Outbound Sales operator | LAT | LAT Start team | Mass | Soft Collector
DR | DR Start team | Mass | Outbound Sales operator | LAT | LAT Start team | Mass | Hard Collector
DR | DR Start team | Mass | Customer Support operator | LAT | LAT Start team | Mass | Hard Collector
DR | DR Start team | Mass | Customer Support operator | LAT | LAT Start team | Manager | IT Manager
DR | DR Start team | Mass | Inbound Sales operator
DR | DR Start team | Mass | Inbound Sales operator
DR | DR Start team | Manager | Head of HR Section

## _
BusinessLines
Product&BP
Digital Sales
Marketing
Risk
IT
HR
Finance
Legal
Operations